## Sheet1
Change ID | Data Element/Class/Type | Cardinality | Type | Element Definition | Examples | Change | Change Rationale | Proposed By | Grouping Concept | Decision | Decision Date | Decision Rationale | Comments | Implemented in Model | Implemented in Schema | Implemented On | Implemented By | Reviewed By | Reviewed On | Status | Phase
AE-1 | criticality | n/a | n/a | The clinical importance or seriousness of the adverse event. E.g., life-threatening, potentially requires hospitalization, self-resolving. Different from severity in that a moderate subarachnoid hemorrhage is likely to be highly important, whereas a moderate headache is not. | life-threatening, potentially requires hospitalization | Rename to 'importance' | In this case, critically (routine, urgent, stat) is semantically overloaded. The actual intent of this data element is to describe the clinical importance or seriousness of the adverse event - life-threatening, potentially requires hospitalization. | Mark Roche Victor Lee | AdverseEvent | Pending Review | 2013-03-11 |  | HeD terminology group requested this change. | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
AS-1 | isValid | Optional (0-1) | BL | Primarily designed to support analysis of previous immunizations. | n/a | Move from SubstanceAdministrationEvent to AdministrableSubstance. | Validity of a shot may be partial if there is more than one antigen in the immunization event and it was administered with the proper waiting period for one antigen but too soon for the other. | David Shields | AdministrableSubstance | Deferred for Phase 2 | 2013-03-08 | Seek feedback from immunization registry experts. |  | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
AS-2 | validAdministrationTimeInterval | Optional (0-1) | IVL_TS | Acceptable time for administering the substance. Distinct from proposedAdministrationTimeInterval that this time includes acceptable but suboptimal administration times. This is an important aspect of immunizations, which have recommended and acceptable/valid timeframes for administration that can differ. |  | Move from SubstanceAdministrationProposal to AdministrableSubstance. | Validity of a shot may be partial if there is more than one antigen in the immunization event and it was administered with the proper waiting period for one antigen but too soon for the other. | David Shields | AdministrableSubstance | Deferred for Phase 2 | 2013-03-08 |  | Seek feedback from immunization registry experts. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
BS-1 | bodySiteCode | Optional (0-1) | CD |  |  | Make bodySiteCode optional rather than required. | body site may be specified in the procedure code. Hence, we need a way to express laterality alone as well. | David Shields | BodySite | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CDS-1 | cdsSubTopic | Optional (0-1) | CD | Narrows down the knowledge request by specifying a subdomain of interest (e.g., indications, contraindications, dose). | Indications, Contraindications, Dose | Add to cdsContext | To harmonize with InfoButton | Howard Strasberg | CdsContext | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. | Needed to support infoButton Rules | Yes |  |  | Claude Nanjo |  |  | Pending Review | Phase 1
CDS-2 | cdsEncounterType | Optional (0-1) | CD | The type of patient encounter (e.g., inpatient, outpatient) in which the knowledge request takes place. Encounter type (Value set: ActEncounterCode [2.16.840.1.113883.1.11.13955]) | Inpatient, Outpatient | Add to cdsContext | To harmonize with InfoButton | Howard Strasberg | CdsContext | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. | Needed to support infoButton Rules | Yes |  |  | Claude Nanjo |  |  | Pending Review | Phase 1
CDS-3 | attribute | Optional, Multiple (0-*) | CodedNameValuePair | A user-specified attribute for this class. The field 'attribute' supports user-defined attribute extensions for CDS contexts. New concepts defined in this manner need to have an associated template. Refer to Implementation Guide for details. |  | Add to cdsContext | To support extension of the CDS context when necessary. | Claude Nanjo | CdsContext | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. | There are use cases where the CdsContext may need to be extended for point-to-point communication or to handle non-standard use cases for instance. | Yes |  |  | Claude Nanjo |  |  | Pending Review | Phase 1
CDS-4 | concept of unknown | n/a | n/a |  |  |  |  | Howard Strasberg | General | Rejected | 2013-03-07 | Out of scope of the vMR. Addressed by HeD expression language. | How does one represent unknown in rules. The HeD expression language supports the representation of 'no information found or provided' using the isNull expression. This addresses this concern raised by Howard. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
CDS-5 | templateId | Optional (0-1) | II | n/a |  | Change type from II to CodedIdentifier for both CdsInput and VMR class | Supports the association of a concept with a template. | David Shields | CdsInput | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CHEMO-1 | ChemotherapyProposal | n/a | Extends SubstanceAdministrationProposal | Proposal to represent a chemotherapy regiment |  | Add ChemotherapyProposal | Common order type | Victor Lee | ChemotherapyProposal | Deferred for Phase 2 | 2013-03-11 | Placeholder for Phase II. |  | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
CIV-1 | diluent | Optional, Multiple (0-*) | SubstanceAdministrationProposal | A fluid base (sometimes called a "base solution") into which an additive is mixed in order to prepare IV fluids for patient administration; the diluent is an inactive ingredient | D5W | ComplexIVProposal | A complex IV may contain one or more diluent | Aziz Boxwala | ComplexIVProposal | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CIV-2 | additive | Optional, Multiple (0-*) | SubstanceAdministrationProposal | An active ingredient that is mixed with a diluent; the diluent enables intravenous delivery of the additive to a patient | dopamine | ComplexIVProposal | A complex IV may contain one or more additive. | Aziz Boxwala | ComplexIVProposal | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-0 | id | n/a | n/a | A unique ID of this clinical statement for reference purposes. Does not need to be the actual ID of the source system. While id is optional in this model to support ID assignment post-creation in some use cases, when defined, a ClinicalStatement will require the eventual assignment of a unique ID. |  | Update definition of 'id'. | ID was made optional in the model but is a required field. Optionality is required in some use cases where assignment of the ID is done at a later time. However, once defined a CS requires an id. | Kensaku Kawamoto | ClinicalStatement | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-1 | ClinicalStatement | n/a | n/a | n/a | n/a | ClinicalStatement is currently an abstract class in the model. Change it to make it a concrete class. | This requirements allows for the definition of new classes in addition to attribute extension. Coupled with the the new 'attribute' extension approach, making ClinicalStatement a concrete class would support the creation of new concepts not defined in the model and outside the predefined hierarchy proposed by the vMR. From Bernadette Minton: "In order to facilitate point-to-point exchange of knowledge artifacts, the Clinical Statement Type was made concrete. This allows a content producer to create knowledge artifacts in a structure specific to the needs of a given consuming system. It is important that this mechanism only be used as a last resort, when there is no other type that meets the needs of the consuming system (this should be made clear in the IG). I.e., if an existing type can be extended to meet the needs of the consuming system, it should be used instead. Instances of Clinical Statement Type should only be used when none of the existing types are appropriate for consumption by the consuming system. " | Kensaku Kawamoto Bernadette Minton | ClinicalStatement | In-Scope for Phase 1 | 2013-03-13 | This change may not be needed because most concept base types appear to have been defined and align with the RIM (Aziz). However, before excluding this change definitely, we will need to discuss the need further during Phase 2 and the approach. We also need to evaluate whether we need a new hierarchy for the QDM 'Intervention' category as these are not really procedures. | It should be made clear, however, that this mechanism will prevent interoperability and is therefore highly discouraged. | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-3 | templateId | Unchanged | CodedIdentifier | n/a | n/a | ClinicalStatement/templateId type has been changed to CodedIdentifier. CodedIdentifier extends II and adds a relevantConcept (CD). (Refer to CS-2 for additional information). | A template, in the context of a ClinicalStatement, should have a human readable name and specify the code of the concept it defines. | Claude Nanjo | ClinicalStatement | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | During our call, we discussed losening the restriction on II to allow identifierName. The type should be String and not ST due to the extra baggage ST brings. In the schema, this type will be xs:string. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-4 | attribute | Optional, Multiple (0-*) | CodedNameValuePair | A user-specified attribute for this class. The field 'attribute' supports user-defined attribute extensions for clinical concepts. New concepts defined in this manner need to have an associated template. Refer to Implementation Guide for details. | n/a | The 'attribute' has been added to the ClinicalStatement class. It has cardinality 0-* and is of type CodedNameValuePair. | This change allows a more intuitive extension mechanism for the addition of attributes to concepts in the vMR that does not semantically overload the notion of an ObservationResult. It has been added to address an HeD ballot disposition. | Claude Nanjo Aziz Boxwala Bernadette Minton | ClinicalStatement | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | Question: What if one specifies an additionalAttribute that is equivalent to an explicitly stated attribute. How do we specify their equivalence? During our call, we proposed providing guidelines in the specification on how to name attributes and assign value sets to them to support semantic equivalence and achieve easier readability (Victor). | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-5 | ClinicalStatement.type ClinicalStatement.subType | Optional (0-1) | CD | n/a | n/a | Add ClinicalStatement\type and ClinicalStatement\subType. Each are optional (0-1). | These two attributes are to be used to specify the concept represented by this clinical statement and template combination. For instance, type may be a code for Imaging Procedure with Contrast and subType may be a code for Barium Enema. | David Shields Ken Kawamoto | ClinicalStatement | Rejected | 2013-03-04 | This is duplicative with ProcedureCode. Furthermore, it is generally bad practice to specify the parent type if it can be inferred by subsumption. Templates will have an associated code in the context of the ClinicalStatement. Refer to CS-2. | Templates will be revisited during Phase 2. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
CS-6 | evaluatedPersonId | Optional (0-1) | II | The 'owner' of this clinical statement. | n/a | Add to ClinicalStatement | This attribute of ClinicalStatement would support bidirectional navigation in the vMR. For instance, a patient object knows about its clinical statements. However, the clinical statements for this patient are not aware of the patient for which they are defined. This is an important requirement when one looks at flattened data. | David Shields Aziz Boxwala Davide Sottara | ClinicalStatement | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. | Note, this relationship can be inferred. However, here we are stating it explicitly. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-7 | id | Optional (0-1) | II | n/a | n/a | Change to optional. | The base ClinicalStatement type in the vMR requires an id element. This requirement results in significant noise in the ActionSentences because in order to validate, they have to have an id, but the actions have no way of producing those ids, nor should they. | Bryn Rhodes | ClinicalStatement | In-Scope for Phase 1 | 2013-03-05 | Be sure to make ID required in some areas - In IG or template. For list, you need ID - flattened use case. | [David Shields] 1. In regard to ID: a. We made ID required, because in inferencing we need a way to reference each class when there are related classes. Making ID required is generally an HL7 v3 standard, except for the “trivial observation” class. i. A less-important additional reason was that a system might need to tie inferencing responses back to particular data elements in their database, and the ID would furnish a way to do that. b. However, in using the vMR, these ID elements are often created (e.g., in SQL, or in Mirth, or in program code) as UUID/GUID values which have no particular intrinsic tie-back value. i. Furthermore, it is easy in inferencing application code to populate the ID value if it is missing. 1. However, this will break in situations where the data in the vMR schema is furnished in a flattened form, by submitting all or some clinical statements in a flat list structure, and the relationships in another flat list structure which links the clinical statements by their ID values. a. The flat list structure is supported in particular for use cases where a particular entity or clinical statement is referenced repeatedly by other entities or clinical statements. The ability to furnish it once, and then reference it elsewhere can support far more compact vMR data instances. This can have a big impact on performance for use cases that do things like scanning a patient’s complete electronic medical record, where elements such as the certifications of a provider and/or the place of service, etc. are required for the logic of the rules, but are drawn from a relatively short list. c. I think I would support making the ID value optional (conditional), with a big explanatory caution note saying it should always be furnished for listed data structures, and is recommended for nested data structures, but may be omitted for conciseness when that is useful (or other language to that effect). | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CS-8 | relationshipToSources | Optional, Multiple (0-*) | RelationshipToSource | Collection of ClinicalStatements that specific this ClinicalStatement as target of relatedClinicalStatement relationship. |  | Add to ClinicalStatement a new attribute called 'relationshipToSources'. This should be of type 'RelationshipToSource' and specify two required attributes: sourceId(II) and relationshipToSource(CD). | This requirement has been proposed to support easier bidirectional navigation especially when dealing with lists of Clinical Statements. | David Shields Davide Sottara | ClinicalStatement | Deferred for Phase 2 | 2013-03-05 | Let us define clear use cases to support this change as it may be more of an implementation detail rather than a requirement for information exchange. |  | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
CS-9 | InterventionProposal | n/a | n/a | An intervention that does not require physical contact with the patient - e.g., patient education. | Patient Education | Add to the vMR. | vMR may need the concept of an Intervention as defined by QDM to represent clinical statements such as those related to Patient Education. | David Shields, Claude Nanjo | ClinicalStatement | Deferred for Phase 2 | 2013-03-08 | Need additional feedback from Quality Measure Community. | Pending comments from Aziz based on work with Partners. Pending comments from the QDM community. This may, in fact, be a Phase 2 requirements, in which case it will be deferred. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
DOC-1 | Documentation | n/a | n/a | This type may be used to represent documentation that is either free text or richer in format (e.g., XML or HTML) where provenance is not relevant. The type of the documentation is determined by a code that represents the type of documentation ("e.g., a consult note, a provider instruction, a patient instruction, etc...). It is intended to represent comment fields and notes such as those associated with order entry forms. Either freeTextValue or content must be specified. |  | Add new Documentation type to the vMR. Documentation has a type (CD) that defines the type of comment made (e.g., provider instruction, patient instruction, etc...). It also has a freeTextValue to hold the free text value of the comment (Optional). It also has a 'content' attribute of type ED to support other mime-types (Optional) | vMR needs a type to represent document attributes of either text or ED. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DOC-2 | type | Required (1-1) | CD | Code that specifies the type of document represented: E.g., 'Instructions to Provider', 'Patient Instructions', 'Special Handling', etc... | 'Instructions to Provider', 'Patient Instructions', 'Special Handling', etc... | Add to Documentation type. | Refer to DOC-1 and PP-3 for additional information. | Claude Nanjo | Documentation | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DOC-3 | freeTextValue | Optional (0-1) | string | The free text representation of this document. | n/a | Add to Documentation type. | Refer to DOC-1 and PP-3 for additional information. | Claude Nanjo | Documentation | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DOC-4 | content | Optional (0-1) | ED | The content of this document in encapsulated data format. The intent of this attribute is to support content with formatting such as XML and XHTML. | n/a | Add to Documentation type. | Refer to DOC-1 and PP-3 for additional information. | Claude Nanjo | Documentation | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DP-1 | dietQualifier | Optional, Multiple (0-*) | DietQualifier | Diet proposals may be fully precoordinated in a terminology or specified by type only and allowing the qualifiers (eg, specification of calories, carbohydrates, protein, fat, sodium, potassium, etc.) to be post-coordinated. | Salt = 2 grams Salt = 'Low Sodium' Fluid Consistency = 'Honey Thick Liquids' | Add to DietProposal. | Allows the representation of many diet qualifiers like nutrients, fluids, etc... | Victor Lee | DietProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DQ-1 | dietQualifierType | Required (1-1) | CD | The type of nutrient that this diet contains. Nutrient types include: carbohydrates, lipids and fats, salts such as Sodium or Potassium, fibers, and also fluids. | Carbohydrate, fiber, fluid, fat, etc... | Add to DietQualifier | Needed to specify the type of nutrient. | Claude Nanjo | DietQualifier | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DQ-2 | amount | Optional (0-1) | IVL_PQ | The quantity of nutrient or bound to consider for this diet. For instance, 40mg, <40mg, 30mg<x<60mg, etc... |  | Add to DietQualifier | Needed to specify the amount of the nutrient in this diet. | Claude Nanjo | DietQualifier | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DQ-3 | qualifier | Optional (0-1) | CD | Not all nutrients will be given using physical quantities. A fat may be specified as 'Low Fat', 'No Animal Fat', etc... Other examples include: 'Ketogenic 3:1 Ratio', 'Consistent Carb Low (1200-1500 Kcal'), etc... Note that fluid consistencies may also be specified as the qualifier of a Nutrient whose type is 'Fluid'. E.g., Honey Thick Liquids, Nectar Thick Liquids, Pudding Thick Liquids, Other | Low Sodium | Add to DietQualifier | Needed to specify the level of nutrient in this diet | Claude Nanjo | DietQualifier | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DT-2 | Specimen | n/a | n/a | A sample of tissue, blood, urine, water, air, etc., taken for the purposes of diagnostic examination or evaluation. | blood, urine, stool | Add to vMR model as a new type. | Specimen are relevant to both orders and performance measures. | Claude Nanjo | Type | Rejected | 2013-03-08 | Specimen already an 'Entity' in vMR. Simply add an attribute called Specimen Source. | The group felt that Specimen is an important type. As it is already in the model, no need to add. However, we need an attribute for specimen source added to this entity. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DT-3 | DietQualifier | n/a | n/a | Diet qualifier allows the post-coordination of diets in cases where such post-coordination is required. Diets can vary greatly in how they are represented in terminologies. The most common use case for DietQualifier is to represent a nutrient that can be either stated as a quantity, a range, or as a code (e.g., 'Low Protein'). Diet qualifiers may also be such attributes of diet as Dysphagia consistency, Fluid levels and consistency, qualifiers on vegetarian diets, sensitivity or preference, etc.... DietQualifier consists of the dietQualifierType (e.g., Sodium), the amount in the diet (e.g., 20-30g), and/or a qualifier such as 'Low Sodium'. Note that dietQualifierType is required and of type CD. Amount is optional and of type IVL_PQ. qualifier is optional and of type CD. Either amount or qualifier is required and both may not be empty. | {Carbohydrate, <100g, Low Carbohydrate Diet} | Add as new type to model. | Diets often specify specific nutrients. If not already precoordinated in the term, this model allows the specification of such diet qualifiers as either quantity ranges or codes. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. | Claude: This field may be semantically overloaded. Mark Roche is reviewing this concern. May need to alter the definition and restrict to purely nutrients unless the union of Value Sets is supported. | Yes |  |  | Claude Nanjo | Mark Roche David Shields |  | Pending Review | Phase 1
DT-4 | Dose | Optional, Multiple (0-*) | n/a | Class represents the amount of a substance administered as well as the type of dose. For instance, one may administer a loading dose followed by a maintenance dose. | Loading Dose, Maintenance Dose, etc... | The 'Dose' type contains two attributes: administeredQuantity (IVL_PQ) and doseType (CD). The cardinality of doseQuantity is changed from 0-1 to 0-* and doseType shall be removed from SubstanceAdministrationBase. | A given SubstanceAdministrationProposal may have multiple doseQuantities each with a different 'doseType'. For instance, you could have a starting dose, a demand dose, etc... | Claude Nanjo | Data Type | Rejected | 2013-03-13 | Two approaches will be taken for orders that have multiple doses. Either, actually enumerate them (e.g., loadingDose, maintenanceDose) or create separate orders (Oral Steroid Tapering). | Adding multiple doses complicates medication administration when dosingPeriod, frequency, etc... can be different for each dose. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DT-5 | CodedIdentifier | n/a | extends II | An II with an additional code to represent the associated concept. This is relevant for templates that are associated with a particular concept such as Barium Enema for instance. | n/a | Add new type CodedIdentifier that extends II and allows the specification of a relevantConcept (CD) with optional cardinality. | This change was proposed to support the association of a concept that a template defines to a template in the template identifier handle in the Clinical Statement. | Claude Nanjo | ClinicalStatement | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | Should the cardinality be relaxed to Optional Multiple (0-*) in case more than one relevant concept can be associated with a given template. Claude: Does this mean that CdsContext needs to now include a 'templateId'? | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DT-6 | relevantConcept | Optional (0-1) | CD | Code specifying the concept represented by this identifier. | e.g., SNOMED-CT code for Barium Enema (Procedure) | Add an attribute to CodedIdentifier to represent the concept associated with a given II. | This change was proposed to support the association of a concept that a template defines to a template in the template identifier handle in the Clinical Statement. | Claude Nanjo | CodedIdentifier | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | Should the cardinality be relaxed to Optional Multiple (0-*) in case more than one relevant concept can be associated with a given template. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
DTP-2 | dysphagiaConsistency | Optional (0-1) | CD | Needs a good description here: My take is that is a diet qualifier. If it is though, we need to document thoroughly what we mean by diet qualifier as it may be more than just a nutrient like fat, carbohydrate, etc... It may include things like fluids and their consistency, dysphagia consistency, etc... |  | Add to DietProposal. | Need to be able to represent diet qualifiers such as diet consistency, nutrient levels, sensitivity, etc... | Claude Nanjo | DietProposal | Rejected | 2013-03-07 | Handled using diet qualifier. Group decided to use a more general approach to diet in order to support the wide range of representations of diet. As we learn more about diets, we may need to then specify additional common fields. | My take is that is a diet qualifier. If it is though, we need to document thoroughly what we mean by diet qualifier as it may be more than just a nutrient like fat, carbohydrate, etc... It may include things like fluids and their consistency, dysphagia consistency, etc... | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DTP-3 | vegetarianDietType | Optional (0-1) | CD | Vegan, Vegetarian, Vegetarian Lacto, Vegetarian Lacto Ovo |  | Add to DietProposal. | Need to be able to represent diet qualifiers such as diet consistency, nutrient levels, sensitivity, etc... | Claude Nanjo | DietProposal | Rejected | 2013-03-07 | Handled using diet qualifier. Group decided to use a more general approach to diet in order to support the wide range of representations of diet. As we learn more about diets, we may need to then specify additional common fields. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DTP-4 | sensitivity | Optional (0-1) | CD | Gluten Free, Lactose Free, Latex Allergy, Low Lactose, MAO Inhibitor Allergy, Milk Free, No Caffeine, No Citrus, No Eggs, No Iodine, No Peanuts, No Pork, No Red Meat, No Shellfish, No Soy Products, Other, Pregnant, Vegetarian, Wheat Free |  | Add to DietProposal. | Need to be able to represent diet qualifiers such as diet consistency, nutrient levels, sensitivity, etc... | Claude Nanjo | DietProposal | Rejected | 2013-03-07 | Handled using diet qualifier. Group decided to use a more general approach to diet in order to support the wide range of representations of diet. As we learn more about diets, we may need to then specify additional common fields. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DTP-5 | preference | Optional (0-1) | CD | Gluten Free, Kosher, Lactose Free, Latex Allergy, Low Lactose, Milk Free, No Caffeine, No Citrus, No Eggs, No Iodine, No Peanuts, No Pork, No Red Meat, No Shellfish, No Soy Products, Other, Pregnant, Vegetarian, Wheat Free |  | Add to DietProposal. | Need to be able to represent diet qualifiers such as diet consistency, nutrient levels, sensitivity, etc... | Claude Nanjo | DietProposal | Rejected | 2013-03-07 | Handled using diet qualifier. Group decided to use a more general approach to diet in order to support the wide range of representations of diet. As we learn more about diets, we may need to then specify additional common fields. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
DTP-6 | ketogenic | Optional (0-1) | CD | Ketogenic 3:1 Ratio, Ketogenic 4:1 Ratio, Ketogenic Diet, Ketogenic Full |  | Add to DietProposal. | Need to be able to represent diet qualifiers such as diet consistency, nutrient levels, sensitivity, etc... | Claude Nanjo | DietProposal | Rejected | 2013-03-07 | Handled using diet qualifier. Group decided to use a more general approach to diet in order to support the wide range of representations of diet. As we learn more about diets, we may need to then specify additional common fields. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
E-1 | evaluatedPersonId | Optional (0-1) | II | The person referencing this entity, generally the patient. | n/a | Add to Entity in model (EntityBase in Schema) | To support bidirectional navigation. | David Shields Ken Kawamoto | Entity | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | Add to EntityBase in XSD | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
E-2 | attribute | Optional, Multiple (0-*) | CodedNameValuePair | A user-specified attribute for this class. The field 'attribute' supports user-defined attribute extensions for entities. New concepts defined in this manner need to have an associated template. Refer to Implementation Guide for details. | n/a | The 'attribute' has been added to the Entity class. It has cardinality 0-* and is of type CodedNameValuePair. | This change allows a more intuitive extension mechanism for the addition of attributes to concepts in the vMR that does not semantically overload the notion of an ObservationResult. | Ken Kawamoto | Entity | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. | Add to EntityBase in XSD | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
EB-1 | encounterType | Required (1-1) | CD | Identifies the type of encounter with as much specificity as available, or as required by a template. E.g., outpatient encounter, outpatient cardiology encounter. |  | Make encounterType optional in EncounterEvent. | This may be required for patient-reported data, where a patient might say "I saw Dr. Smith last November for pain in my chest" In this use case, there might not be a recorded EncounterType, but you still might want to record the fact of the encounter and its (possibly approximate) dates, and possibly include it in a CDS evaluation. | David Shields | EncounterEvent | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. | TO DAVID: encounterType would need to be made optional in EncounterBase. Is this okay as it impacts all other encounter subclasses. | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
E-3 | id | Required (1-1) | II | n/a |  | Change from required to optional. | Need to make optional to support the use case where the id is set some time later after creation. | David Shields | Entity | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
E-4 | templateId | Optional (0-1) | II | n/a |  | Change type from II to CodedIdentifier |  | David Shields | Entity | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
GB-1 | targetGoalValue | n/a | ANY | n/a | n/a | Change from xsd:Choice to dt:ANY | Use xsiType rather than choice to facilitate implementation using polymorphism rather than switch. | Aziz Boxwala | GoalBase | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | n/a | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
GEN-2 | criticality | n/a | n/a | n/a | n/a | Rename all occurrences of 'criticality' to 'priority' | Priority is the more common way to refer to this concept. | Mark Roche Victor Lee | General | Rejected | 2013-03-13 | Priority too general of a term |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
GEN-3 | clinicalStatements |  |  |  |  | Add new clinical statement subtypes under vmr/patient/clinicalstatements | Needed to make new types available in vMR | Claude Nanjo | ClinicalStatement | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | n/a | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | n/a
GEN-4 | criticality | n/a | n/a | n/a |  | Change all mentions of "Urgency or importance of" to "Urgency of". Disambiguate text where necessary. | Criticality, in its definition overloads the semantics of urgency and importance and is therefore ambiguous. From a terminology point-of-view, this is problematic in the sense that two quite different value sets may apply to this one field. Since often urgency is the intended meaning, urgency was retained. If importance is the intended meaning, it may need to be added alongside criticality (see GoalBase) or instead of criticality (see AdverseEvent) | Mark Roche Victor Lee | General | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IE-1 | radiationDose | Optional (0-1) | IVL_PQ | The total dosage of radiation received during a procedure or diagnostic test. |  | Add to ImagingEvent/radiationDose | QDM requires the documentation of radiation dose. | QDM | ImagingEvent | Deferred for Phase 2 | 2013-03-07 | Need more time to do this right and ensure that Quality folks can help define approach. |  | No | No | n/a | n/a | n/a | n/a | Deferred | Phase 2
IE-2 | radiationDuration | Optional (0-1) | IVL_TS | The elapsed time (duration) of radiation exposure during a procedure or diagnostic test. |  | Add to ImagingEvent/radiationDuration | QDM requires the documentation of radiation duration. | QDM | ImagingEvent | Deferred for Phase 2 | 2013-03-07 | Need more time to do this right and ensure that Quality folks can help define approach. |  | No | No | n/a | n/a | n/a | n/a | Deferred | Phase 2
IP-10 | isolationCode | Optional (0-1) | CD | Specification for type of precautions that should be taken when in proximity to the patient. For instance, Airborne Precautions, Contact Precautions, Droplet Precautions, Standard Precautions. | Airborne Precautions, Contact Precautions, Droplet Precautions, Standard Precautions | Add to ImagingProcedure | Imaging orders often have this field specified. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-11 | requestedStartDateTime | Optional (0-1) | TS |  |  | Add to ImagingProcedure | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | requestedStartDateTime represents the lower bound of proposedProcedureTime. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-12 | duration | Optional (0-1) | IVL_TS |  |  | Add to ImagingProcedure | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | Duration is represented by proposedProcedureTime. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-1a | contrastType | Optional (0-1) | CD | Specification of the kind of contrast (eg, Barium, Gastrograffin) to be given as part of an imaging proposal. For example, Barium, Gastrograffin. | Barium, Gastrograffin, Per Radiology | ImagingProposal/contrast added to model. It is an optional attribute (0-1) | A number of imaging procedures require contrasting agents. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-11 | The can be constrained in our out if necessary (DbC approach used here). | VL: maybe I have semantically overloaded this data element? Leave as CD element for now, figure out terminology later CN: Should we not just specify the type of contrast assuming that if specified it is Y, if not it is N. Should we add a contrast route? VL: split into 3 data elements (contrast, contrastType, contrastRoute) to avoid semantic overloading | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-1b | contrast | Optional (0-1) | BL | Specification of whether contrast should be administered as part of the imaging study (eg, Yes, No, Per Radiology) | Yes, No, Per Radiology | ImagingProposal/contrast added to model. It is an optional attribute (0-1) | A number of imaging procedures require contrasting agents. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-11 | The can be constrained in our out if necessary (DbC approach used here). | VL: split into 3 data elements (contrast, contrastType, contrastRoute) to avoid semantic overloading | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-1c | contrastRoute | Optional (0-1) | CD | Specification of the route of contrast (eg, Oral, IV, Per Radiology) to be given as part of an imaging proposal | Oral, IV, Per Radiology | ImagingProposal/contrast added to model. It is an optional attribute (0-1) | A number of imaging procedures require contrasting agents. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-11 | The can be constrained in our out if necessary (DbC approach used here). | VL: split into 3 data elements (contrast, contrastType, contrastRoute) to avoid semantic overloading | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-2 | stressor | Optional (0-1) | CD | Type of physiologic or pharmacologic stress that will be subjected to the patient during the imaging procedure. For example, Adenosine, Dipyrdomole, Persantine, Thallium, Cardiolite, Dobutamine, Treadmill. | Adenosine, Dipyrdomole, Persantine, Thallium, Cardiolite, Dobutamine, Treadmill | ImagingProposal/stressor added to model. It is an optional attribute (0-1) | A number of imaging procedures require a stressor agent. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-07 | The can be constrained in our out if necessary (DbC approach used here). |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-3 | requestedStartDateTime | Optional (0-1) | TS | The preferred procedure start date/time. |  | Add to ImagingProposal | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | This field is not needed as we have ProcedureProposalTime which is of type IVL_TS and the lower TS represents perferred procedure start date/time. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-4 | duration | Optional (0-1) | IVL_TS | The duration of the procedure | 8 hrs | Add to ImagingProposal | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | This field is not needed as we have ProcedureProposalTime which is of type IVL_TS. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-5 | portableExam | Optional (0-1) | BL | Designation of whether or not the imaging procedure should be performed at the patient's bedside (Yes) or if the procedure can be conducted in the location of the performing department (No) | Yes, No | Add to ImagingProcedure | Imaging orders often have this field specified. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
IP-6 | reasonForExam | Optional (0-1) | CD | The coded reason for the exam. |  | Add to ImagingProcedure | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | A coded reasonForExam may not be common. This is more often free text and is thus covered by ProcedureProposal.comment. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-7 | requestedFinding | Optional (0-1) | CD | This is used in radiology or lab to ask for a specific thing like an xray to determine the current size of a lesion, etc. |  | Add to ImagingProcedure | Imaging orders often have this field specified. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | Should this be done via separate orders in an order group? Via related clinical statements for observation requests? |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-8 | readingRequest | Optional (0-1) | CD | For imaging if we want another group to read the exam. The purpose of the field is to route the order for documentation. The choices for this field are governed by contract. |  | Add to ImagingProcedure | Represented in CEM orders. | Claude Nanjo | ImagingProposal | Rejected | 2013-03-07 | Group decided to leave this field out. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
IP-9 | transportMode | Optional (0-1) | CD | Specification of how a patient will be moved from their hospital room to the performing department | Patient Bed, Stretcher, Wheelchair, Lift Device, Carried, Crib, Isolette | Add to ImagingProcedure | Imaging orders often have this field specified. | Victor Lee | ImagingProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-1 | II.identifierName | Optional (0-1) | string | A human readable description for this identifier. | Barium Enema Proposal | II has been relaxed to also allow the visibility of identifierName which is present in the underlying ISO specification. It has cardinality 0-1 | Templates need an identifier that also describes in a human readable form the concept that the template represents. This type of identifier could be used for other types of resources but currently, it would be used only in templates in the vMR. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo |  |  | Pending Review | Phase 1
ISO-10 | RTO_PQ | n/a | n/a | A ratio of quantities | 3 mg/5 dcl | Add RTO_PQ to XSD | Ratios of quantities are needed to properly represent medication strengths. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | To David: The way RTO has been implemented in the XSD will not work for RTO_PQ. Currently, the numerator and denominator are in an attribute group (). However, PQ cannot fit in an attribute group so it will have to have two children elements. This will make RTO_PQ different than RTO_INT unless we follow a similar pattern for RTO_INT and move away from the older RTO implementation. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-11 | RTO_INT |  | n/a | A ratio of integers | 3:5 (titers) | Add RTO_INT to XSD | Ratios of integers are needed to properly represent certain types of ratios. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | To David: ATTR_RTO has been modified so that denominator and numerator are no longer 'Decimal' but rather 'xsd:int'. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-2 | RTO | n/a | n/a | n/a | n/a | Change numerator and denominator from PQ to QTY in EA model and remove from schema. | We are encountering several instances where we need an RTO with numerators of type other than PQ. Examples: Strength is a RTO of PQs but Ketogenic is an RTO of ints. Also, PIVL_TS has a frequency field that is a ratio of INT/TS. As there will be more variations in the future, we are deciding to unrestrict RTO and leave it to schema implementation guides and IGs to restrict as necessary. | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-05 | See 'Change Rationale' column. | Need to restrict and modify XSD as necessary. Also need to change wording in description. | Yes | n/a | 2013-03-04 | Claude Nanjo |  |  | Pending Review | Phase 1
ISO-3 | PIVL_TS | n/a | n/a | This type is an ISO21090 type used to represent periodic time intervals and frequencies. Both HeD and the vMR may consider this approach for Phase 2 of the vMR. |  | Add to ISO datatypes for vMR | Consistency of data types with HeD schemata. | Bryn Rhodes | Data Type | Deferred for Phase 2 | 2013-03-08 | vMR needs to address frequency consistently and this cannot be done is that short of a timespan. The group feels that we need to put more thought into this important requirement and defer to Phase 2. | Bryn Rhodes: It's also worth pointing out here that we added the PIVL_TS type to the HeD schema in order to support defining periodic triggers. This type came with some other supporting types as well, and since we're looking at creating a data type-specific namespace that both vMR and HeD Schema will reference, we should probably put those types in at the same time, yes? Question for Bryn: There seems to be two different definition of PIVL_TS. Need to reconcile these before I can add. Group: If this is approved for Phase 1, how do we handle dosingPeriod and dosingPeriodIntervalIsImportant. Question for David Shields: We need to represent frequency consistently in the vMR. Frequencies should be computable but also support codes. Food for thought as we transition to Phase 2. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
ISO-4 | SXCM_TS | n/a | n/a | This type has been defined by HeD. It is the parent type for the PIVL_TS defined in HED. In ISO21090, the parent type is QSET_TS. Reconciliation is required prior to incorporating this type. |  | Add to ISO datatypes for vMR | Parent type of PIVL_TS | Bryn Rhodes | Data Type | Deferred for Phase 2 | 2012-03-08 | vMR needs to address frequency consistently and this cannot be done is that short of a timespan. The group feels that we need to put more thought into this important requirement and defer to Phase 2. | Not sure where this type is defined. Bryn and Claude to reconcile. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
ISO-5 | IVL_PQ/lowValue IVL_PQ/lowUnit IVL_PQ/highValue IVL_PQ/highUnit | Optional (0-1) in EA Required (1-1) in XSD | n/a | n/a | n/a | Make both lower bound and upper bound optional in XSD. Model is fine. | IVL_PQ is an interval (it is the type of doseQuantity), but the highValue and highUnit attributes are required. Is this intended? If not, can we make these attributes optional as well? Also, it's probably worth a review of all the interval types to ensure that they can be open ended. | Bryn Rhodes | Data Type | In-Scope for Phase 1 | 2012-03-08 | See 'Change Rationale' column. | This change only impacts the XSD. The EA UML model is correct. | n/a |  |  |  | Bryn Rhodes |  | Pending Review | Phase 1
ISO-6 | AdministrableSubstance.strength | n/a | RTO | n/a | n/a | Change AdministrableSubstance.strength to be an RTO_PQ. Refer to ISO-2 for more information about this requirement. | Currently strength can only be expressed as a ratio of integers. Yet, the numerator and denominator may not necessary be integers and often have units. A PQ for each numerator and denominator allows the proper representation of Strength. For instance, '120 mg/5 dcl'. | David Shields Bryn Rhodes Claude Nanjo | AdministrableSubstance | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | After change. Denominator and numerator will be elements rather than attributes as PQ is a complex type. | n/a | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7 | ED | n/a | n/a | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | Data Type | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | Note that we have modified this type to by not including 'thumbnail', 'translation', and 'compression'. At this time, these have been commented out of the XML and not physically removed. Also note that schematron instructions have been commented out but are still in the XML. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.1 | value | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.10 | thumbnail | Optional (0-1) | ED | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | Rejected | 2013-03-08 | May not be that relevant in our use case. | Commented out in XML | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
ISO-7.11 | description | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.12 | translation | Optional (0-1) | ED | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | Rejected | 2013-03-08 | May not be that relevant in our use case and sufficiently covered by language. | Commented out in XML | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
ISO-7.13 | integrityCheckAlgorithm | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  | IntegrityCheckAlgorithm simple type added to schema | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.2 | data | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  | Must be xsd:base64Binary | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.3 | mediaType | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.4 | charset | Optional (0-1) | CD | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.5 | language | Optional, Multiple (0-*) | CD | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.6 | compression | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | Rejected | 2013-03-08 | May not be that relevant in our use case. | Commented out in XML | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
ISO-7.7 | xml | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  | Must be xsd:anyType | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.8 | reference | Optional (0-1) | TEL | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-7.9 | integrityCheck | Optional (0-1) | string | See ISO Specification | n/a | Add the ED ISO type to vMR | Allows the representation of richer content. | David Shields | ED | In-Scope for Phase 1 |  |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
ISO-8 | ISO Datatypes | n/a | ISO | ISO Datatypes as a whole |  | Update ISO datatypes based on latest schema revision from HL7. | We need to do this bit of house cleaning to keep vMR consistent with HL7 foundational schemata. | David Shields | Data Type | Deferred for Phase 2 | 2013-03-08 | This requires more work that we can afford for Phase 1. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
ISO-9 | RTO | n/a | n/a | See ISO specification |  | Change in the EA model requires updating the denominator and numerator from PQ to QTY. Remove RTO from XSD and replace with RTO_INT, RTO_PQ which will need to be added to the XSD only. | Currently, the vMR only supports ratios of integers. Strength are ratios of quantities. Yet we do not support this in the XSD (only supports Decimal). | Claude Nanjo | Data Type | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | Commented out. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
LP-1 | specialHandling | Optional, Multiple (0-*) | CD | Special instructions on how to handle a laboratory specimen. For example, 'Keep on ice'. | Keep on ice | Add to LaboratoryProposal | special handling is often an attribute of laboratory proposals. | Victor Lee | LaboratoryProposal | In-Scope for Phase 1 | 2013-03-06 | See Decision Rationale for PP-5 | VL: besides "keep on ice" which might apply to an ABG specimen, I could not think of any other special handling examples. I suspect that the use of this DE will be uncommon. Consider rejecting and require extension to address this? | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
LP-10 | suspectedPathogen | Optional, Multiple (0-*) | CD | The pathogen or pathogens that are felt to be the most likely cause of the patient's condition that led to the laboratory procedure proposal. For instance, Staphylococcus, Streptococcus, Pseudomonas, Neisseria. | Staphylococcus, Streptococcus, Pseudomonas, Neisseria | Add to LaboratoryProposal | Lab orders often have this field specified. | Victor Lee | LaboratoryProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
LP-11 | requestedFinding | Optional, Multiple (0-*) | CD | This is used in radiology or lab to ask for a specific thing like an xray to determine the current size of a lesion, etc. |  | Add to LaboratoryProposal | Found in CEM DCM | Claude Nanjo | LaboratoryProposal | Rejected | 2013-03-07 | Not common and can be addressed in other ways. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-2 | frequency | Optional (0-1) | CD | The interval for between laboratory tests. For instance, TID, BID, q8h, etc... | TID, q8h | Add to LaboratoryProposal | Lab orders often have frequency associated with them. | Claude Nanjo | LaboratoryProposal | Rejected | 2013-03-07 | Moved to ProcedureProposal instead. | Refer to SB-5 (frequency) | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-3 | duration | Optional (0-1) | IVL_TS | The duration of the procedure | 8 hrs | Add to LaboratoryProposal | Lab orders often have this field specified. | Claude Nanjo | LaboratoryProposal | Rejected | 2013-03-07 | This field is not needed as we have ProcedureProposalTime which is of type IVL_TS. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-4 | requestedStartDateTime | Optional (0-1) | TS | The preferred procedure start date/time. |  | Add to LaboratoryProposal | Lab orders often have this field specified. | Claude Nanjo | LaboratoryProposal | Rejected | 2013-03-07 | This field is not needed as we have ProcedureProposalTime which is of type IVL_TS and the lower TS represents perferred procedure start date/time. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-5 | priority | Optional (0-1) | CD |  | Routine, STAT | Add to LaboratoryProposal | Lab orders often have this field specified. | Claude Nanjo | LaboratoryProposal | Rejected | 2013-03-07 | This field is not needed as we have Criticality. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-6 | specimen | Optional (0-1) | Specimen | The source of the collected laboratory specimen | Blood, Sputum, Stool, Urine, CSF | Add to LaboratoryProposal | Lab orders often have this field specified. | Victor Lee | LaboratoryProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
LP-7 | nurseCollect | Optional (0-1) | BL | Should nurse collect specimen | Yes, No | Add to LaboratoryProposal | Lab orders often have this field specified. | Victor Lee | LaboratoryProposal | Rejected | 2013-03-07 | Redundant with collectionMethod (LP-8) and therefore rejected | Seems like this field should be a BL rather than a CD. VL: agree, and I changed it from CD to BL. However, I rejected this DE, see Decision Rationale | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
LP-8 | collectionMethod | Optional (0-1) | CD | Specification of how the laboratory specimen should be obtained | Venous Draw, Arterial Line, Sterile Swab, Nurse Collect, 24-Hour Urine | Add to LaboratoryProposal | Lab orders often have this field specified. | Victor Lee | LaboratoryProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
LP-9 | collectionPriority | Optional (0-1) | CD | Urgency of the laboratory procedure proposal | Routine, Urgent, Stat | Add to LaboratoryProposal | Lab orders often have this field specified. | Victor Lee | LaboratoryProposal | Rejected | 2013-03-09 | VL: Priority/criticality is already addressed in a parent class. CN: Verified and removed from model | Originally included in model but subsequently found to be redundant with DE from parent class (procedureProposal already contained criticality DE) | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
NVP-1 | name | Required (1-1) | CD | A code representing the name of the attribute. | n/a | Added to CodedNameValuePair type. | See change rationale for CS-4. | Claude Nanjo Aziz Boxwala Bernadette Minton | CodedNameValuePair | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
NVP-2 | value | Required (1-1) | ANY | The value of the attribute. | n/a | Added to CodedNameValuePair type. | See change rationale for CS-4. | Claude Nanjo Aziz Boxwala Bernadette Minton | CodedNameValuePair | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
NVP-3 | CodedNameValuePair | n/a | n/a | Class represents a generic Name-Value-Pair object where the name may be controlled by a terminology and the value may be any type deriving from ANY and/or defined by a template. | n/a | Add to vMR as a new data type. This type represents a Name-Value pair whose name is a CD attribute and value is of type ANY. Refer to NVP-1 and NVP-2 for more information about the attributes for this type. | See change rationale for CS-4. | Claude Nanjo Bernadette Minton Aziz Boxwala | Type | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes |  |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
OR-1 | observationValue | Optional (0-1) | ANY | n/a |  | Allow ED as a choice for ObservationResult.observationValue in XSD. | Some observation results may be documents and this use case needs to be supported. | David Shields | ObservationResult | In-Scope for Phase 1 | 2013-03-11 | Need additional input and thought. Also requires an updated way of handling this type in the schema for Phase 2. (i.e., xsi:type referencing. May also be relevant to goals (targetGoalValue). | Used to be out-of-scope but now that observationValue derives from ANY, technically any type can be used unless constrained by templates. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
OR-2 | observationValue | n/a | ANY | n/a | n/a | Change from xsd:Choice to dt:ANY | Use xsiType rather than choice to facilitate implementation using polymorphism rather than switch. | Aziz Boxwala | ObservationResult | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | n/a | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PC-1 | priority | Optional (0-1) | CD | Level of urgency with which the patient care proposal should be carried out | Routine, Urgent, STAT | Add to PatientCare | Often associated with this type of orders. | Claude Nanjo | PatientCareProposal | Rejected | 2013-03-07 | Covered by criticality in ProcedureProposal | Question: Should criticality be renamed to Priority in the context of a lab procedure? Semantic overloading. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PC-2 | frequency | Optional (0-1) | CD | The number of events per interval of time. For instance, TID, BID, q8h, etc... | TID, q8h | Add to PatientCare | Often associated with this type of orders. | Claude Nanjo | PatientCareProposal | Rejected | 2013-03-07 | Covered by frequency in ProcedureProposal | Refer to SB-5 (frequency) | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PC-3 | requestedStartDateTime | Optional (0-1) | TS | The requested starting time for the procedure. |  | Add to PatientCare | Often associated with this type of orders. | Claude Nanjo | PatientCareProposal | Rejected | 2013-03-07 | This field is probably not needed as we have ProcedureProposalTime which is of type IVL_TS and the lower TS represents perferred procedure start date/time. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PC-4 | duration | Optional (0-1) | IVL_TS | The duration of the procedure | 8 hrs | Add to PatientCare | Often associated with this type of orders. | Claude Nanjo | PatientCareProposal | Rejected | 2013-03-07 | This field is probably not needed as we have ProcedureProposalTime which is of type IVL_TS. | May need to add note in IG | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PCA-1 | lockoutInterval | Optional (0-1) | IVL_PQ | The amount of time that must elapse after a PCA demand dose is administered before the next PCA demand dose can be delivered. For example, 10 minutes | 10 minutes | Added under PCA class. PCA orders often define a lockout interval where a physician needs to be consulted prior to admistering the demand dose. | Common PCA proposal field. | Victor Lee | PCA | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | VL: discuss with community regarding whether to leave in PCA subclass or move to parent class of Substance Administration Proposal Claude: We decided to leave it in. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PCA-2 | doseLimit | Optional (0-1) | RTO_PQ | The maximum amount of a PCA drug that can be delivered within a certain time window. For example, 50 mg/4 hours | 50 mg/4 hours | Get def from Victor Lee. VL: renamed DE from "timeLimit" to "doseLimit" | Common PCA proposal field. | Victor Lee | PCA | Rejected | 2013-03-11 | Redundant with SAP doseRestriction | This attribute seems redundant as SAP defines a doseRestriction. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PCA-2 | loadingDose | Optional (0-1) | IVL_PQ | The initial amount of an analgesic to be administered at one time. |  | Add under PCA class. | Common PCA proposal field. | Victor Lee | PCA | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PCA-3 | demandDose | Optional (0-1) | IVL_PQ | A dose of an analgesic given in addition to the specified basal rate; usually delivered in response to an action such as a patient pressing a button that communicates with a PCA pump |  | Add under PCA class. | Common PCA proposal field. | Victor Lee | PCA | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PE-1 | ImagingEvent | n/a | extends ProcedureEvent | The actual event of performing an Imaging Procedure. |  | Add ImagingEvent to vMR as an extention of the vMR ProcedureEvent. | Add ImagingEvent to vMR to hold radiationDose and radiationDuration needed by the QDM. It has not been added to superclass ProcedureEvent because it is specific to Imaging. It has not been added to ProcedureProposal as this information is often not part of a typical order. | QDM | ProcedureEvent | Deferred for Phase 2 | 2013-03-07 | This class requires the input of the Quality Measure Community. Adding it now is premature. | After an email exchange with Chris Millet, we might consider taking this out of scope for Phase 1 and defer it to Phase 2. | Yes |  |  | Claude Nanjo |  |  | Deferred | Phase 2
PO-1 | patientOnIV, patientIsPregnant, patientHasBreastImplants, patientHadPreviousMastectomy, patientHasMetalImplants, cardiacEnzymesPending, and patientOnOxygen | Optional (0-1) | BL | Patient characteristics |  | Add to ProcedureOrder or subclasses. | Some procedures may need to be performed or interpreted as a function of the patient. | Claude Nanjo | ProcedureOrder | Rejected | 2013-03-04 | This is better achieved either via a related Clinical Statement with ObservationRequest for proposal and ObservationResult for orders. It could also be achieved as specific observation requests in an ActionGroup in an HeD knowledge document (Aziz). |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PP-1 | originationMode | Optional (0-1) | CD | The mode the order was received (such as by telephone, electronic, verbal, written). This describes 'how' the communication was done as opposed to dataSourceType which specifies the 'where' and 'from'. | Telephone, verbal, written, electronic | Add originationMode to ProcedureProposal. | Defined in CIMI model. Describe how the order proposal was received. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | Here we discussed how originationMode differs from dataSourceType. The datasource if often needed for CDS - who asked for this order. It lends weight to the request. OriginationMode specifies the 'how'. How was it communicated? | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-10 | LaboratoryProposal | n/a | n/a | A proposal for a laboratory test. | CBC with automated WBC differential | Add LaboratoryProposal by extending ProcedureProposal | Laboratory procedures are a common class of procedure orders. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-11 | RespiratoryCareProposal | n/a | n/a | Order proposals that encompass supplemental oxygen (eg, nasal cannula, face mask), BiPAP/CPAP, and mechanical ventilation. While these are vastly different respiratory care concepts, the associated data elements can be constrained through templates. | Nasal Cannula, Face Mask, BiPAP, CPAP, Mechanical Ventilation | Add RespiratoryCareProposal by extending ProcedureProposal | Respiratory Care procedures are a common class of procedure orders. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-12 | frequency | Optional (0-1) | CD | The interval in between events. For instance, TID, BID, q8h, etc. | TID, q8h, qac | Added to Procedure Proposal | Procedure proposals often specify the frequency for action within some duration. This attribute was missing. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-13 | timing | Optional (0-1) | CD | Timing relative to some event. Today, Tomorrow, On Admission to ICU, etc... | Today, Tomorrow, On Admission to ICU, On Call To Operating Room | Added to Procedure Proposal | Procedure proposals often specify the timing for action. This attribute was missing. | Howard Strasberg | ProcedureProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. | VL: While I think that most of the common timing code set values can be codified, there might be some uncommon timing specifications that I would be surprised to find comprehensively addressed by standard terminologies (eg, "1-2 hours after vancomycin dose") so I wonder if there is a way to capture free text timing specifications in addition to the CD element? | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-14 | prnReason | Optional, Multiple (0-*) | CD | Indication for the proposed procedure such as shortness of breath; Reasons such as "SpO2 less than x%" should be addressed as a PRN Instruction rather than a PRN Reason as it is unlikely that a value set can be identified for such range of possible observations. For example, Pain, Shortness of Breath, Insomnia, Nausea. | Pain, Shortness of Breath, etc. | Add to ProcedureProposal | PRN Reason is a common 'cross-cutting' attribute. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. | Please note the proposed usage for PRN Reason. PRN Reason is a coded field. For most cases this is a valid assumption. In some cases, the PRN Reason may be based on some observation of the patient and could be stated in either free text or as a related observation. In these cases, the PRN Reason value set should offer a choice of 'Other' and either a comment of type 'PRN Instruction' or a related clinical statement of type 'PRN Reason' should be associated with this proposal. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-15 | proposedProcedureTime | n/a | IVL_TS | n/a | 2 hours | Make a PQ to capture duration | For a procedure proposal, should the proposed procedure time not be a duration rather than a time interval? Afterall, it will never be calendared at that point. | David Shields Claude Nanjo | ProcedureProposal | Rejected | 2013-03-11 | proposedProcedureTime may be populated by CDS Services as calendar times based on patient record. | Should this be a duration rather than an IVL_TS. Briefly putting in scope to discuss on Monday. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PP-2 | orderJustification | Optional (0-1) | CD | Taken from CIMI: OrderJustification is a component model. Order Justification lists any required items to explain the why's of the order. This is not a semantic link because the justification is made at the time of the order by the practitioner and alterable by the practictioner. Billing may use this justification, but billing cannot create this justification. Any justification created in the billing use cases will need to be of a different structure. Current values for the key domain are: Diagnosis, Signs and Symptoms, ?Health Issue. Action in the application will be: A practictioner may choose justification from a list or from the problem list of the patient. If the practictioner chooses a problem from a list then the application will ask: do you want to add this to the patient's problem list? If yes then the problem will be create in a model structure, if no then the ecid for the Health Issue will be stored. Because the Health Issue domain is not sub categorized we perform the categorization of the health issue via the key domain chosen. This way the order application and the data mining efforts can find what kind of thing this is being used as. Kind of a role. The otherwise error line exists because this model is meant for application use and should have an expectation of what is allowed. |  | Add orderJustification to ProcedureProposal | Often a proposal is backed by information about the patient. For instance, a proposal may be justified by a problem from the patient record. | Claude Nanjo | ProcedureProposal | Rejected | 2013-03-06 | This is already addressed in the vMR using related clinical statements. Note that even the CIMI description describes such an approach. The group agrees that related clinical statements is a more elegant approach than simple codes. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PP-3 | comment | Optional, Multiple (0-*) | Documentation | A comment, instruction, or note associated with the proposal. The type specifies the type of comment (e.g., 'Provider Instruction', 'Patient Instruction', 'Reason for Procedure', 'Consult Note', etc...) and the value of the comment represents the free text value. | provider instructions, patient instructions, notes, reason, consult notes, etc... | Add comment to ProcedureProposal. Make type of comment 'Document' and introduce 'Document as a new type. | Order proposals often have associated comments. Comments may be addressed to different target audiences and thus a comment type provides additional information about the purpose of the comment. A comment can be restricted to be free text in a template or could support other formats such as XML, PDFs, etc.... | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | General way to represent comments of various types. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-4 | providerInstruction | Optional, Multiple (0-*) | string | From CIMI: ProviderInstruction This field contains the ordering provider's instructions to the patient or the provider administering the drug or treatment. (HL7 definition, RXE-7) This is called Directions in Centricity Pharmacy which creates an English translation of the dose and frequency which then can be added to or changed by the pharmacist. | n/a | Add to ProcedureProposal | Provider Instructions is a common attribute of orderables. | Claude Nanjo | ProcedureProposal | Rejected | 2013-03-06 | Can be modeled more generically using the Documentation type. Refer to PP-3 for more information about this approach. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PP-5 | specialHandling | Optional, Multiple (0-*) | CD | From CIMI: SpecialHandling Built to accomodate special conditions in execution of the order. Particularly in transportation and radiology type orders. Such as diabetes, fractures(s), fragile skin, Isolation, No special handling, nurse to assist, etc... | diabetes, fractures(s), fragile skin, Isolation, No special handling, nurse to assist, etc... | Add to ProcedureProposal | special handling is often an attribute of procedure proposals. | Claude Nanjo | ProcedureProposal | Rejected | 2013-03-06 | As defined by CIMI, the group felt that specialHandling is semantically overloaded. The concept is already captured by the fields transportMode and isolationCode as non-overloaded attributes of Imaging. Since special handling can also apply to specimens, we opted to move this attribute to LaboratoryProposal in order to support more focused value sets. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
PP-6 | orderStatus | Optional (0-1) | CD | From CIMI: The purpose of this element is to support workflow. The domain for this qualifier is the same across all orders, but may be a constrained domain in each subtype (e.g., the workflow on a lab order may be different from the workflow for medication orders. Need to get HL7's State Diagrams for orders to inform values for this domain. | VL: I am not sure about examples | Add to ProcedureProposal | The purpose of this element is to support workflow. | Victor Lee | ProcedureProposal | Deferred for Phase 2 | 2013-03-11 | See 'Change Rationale' column. VL: I cannot think of a use case for this data element, as I've never had to specify when entering orders. Even if there is a use case, it might be uncommon enough that we'd ask implementers to use an extension mechanism to capture. | Omit for Phase 1, reconsider for Phase 2 if there is a use case defined by the community | No | No | n/a | n/a | n/a | n/a | Deferred | Phase 2
PP-7 | ImagingProposal | n/a | n/a | A proposal for an Imaging Order. For instance, Chest Radiograph - PA and Lateral. | Chest Radiograph - PA and Lateral | ImagingProposal added to model. ImagingProposal subclasses ProcedureProposal | Most CPOE systems have forms to represent imaging procedures. There are sufficient numbers of fields specific to Imaging that it warrants its own subclass. | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
PP-8 | PatientCareProposal | n/a | n/a | A Nursing/Patient Care order | Turn patient every 2 hours, Strict Ins and Outs, Fall Precautions, Elevate Head of Bed to 30 Degrees | Add PatientCareProposal by extending ProcedureProposal. | Patient Care orders are a common class of procedure orders. | Victor Lee | ProcedureProposal | Deferred for Phase 2 | 2013-03-13 | Need more investigation of Nursing Orders |  | No | No |  |  |  |  | Deferred | Phase 2
PP-9 | DietProposal | n/a | n/a | A class representing a wide variety of allowable types of meals and/or specification of meal and/or nutrient restrictions for an individual patient, based on the patient's clinical condition | Regular Diet, Calorie-Controlled Diet, 2-gram Sodium Diet | Add DietProposal to model by extending ProcedureProposal | Diet orders are a common class of procedure orders | Victor Lee | ProcedureProposal | In-Scope for Phase 1 | 2013-03-04 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-1 | EPAP | Optional (0-1) | IVL_PQ | Expiratory positive airway pressure, often expressed in cmH20 in the United States. Example: 5 cmH2O | 5 cmH2O | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-10 | ventilatorMode | Optional (0-1) | CD | Primary setting on a mechanical ventilator that specifies how machine breaths will be delivered to a patient. Examples:Assist Control (AC), Synchronized Intermittent Mandatory Ventilation (SIMV), Pressure Support Ventilation (PS or PSV), Pressure-Regulated Volume Control (PRVC) | Assist Control (AC), Synchronized Intermittent Mandatory Ventilation (SIMV), Pressure Support Ventilation (PS or PSV), Pressure-Regulated Volume Control (PRVC) | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-11 | oxygenDeliveryMethod | Optional (0-1) | CD | Describes how oxygen will be delivered to a patient. For example: Nasal Cannula, Hood, Face Mask, Non-rebreather Mask | Nasal Cannula, Hood, Face Mask, Non-rebreather Mask | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  | Changed "deliveryMethod" to "oxygenDeliveryMethod"; do not use procedureMethod to represent oxygen delivery method | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-12 | isolationCode | Optional (0-1) | CD | Describes the kinds of precautions that should be taken for the patient. Values include: Airborne Precautions, Contact Precautions, Droplet Precautions, Standard Precautions, Neutropenic (Reverse) Precautions | Airborne Precautions, Contact Precautions, Droplet Precautions, Standard Precautions, Neutropenic (Reverse) Precautions | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-13 | frequency | Optional (0-1) | CD | The frequency of the event or procedure | TID, q8h, qac | Add to RespiratoryCareProposal | n/a | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-07 | Questionable use case and moved to ProcedureProposal. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-14 | requestedStartDateTime | Optional (0-1) | TS | Desired start time for procedure. |  | Add to RespiratoryCareProposal | n/a | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-07 | Typically respiratory orders are intended to be proposed for RIGHT NOW as opposed to some point in the future. Also redundant - addressed by attribute proposedProcedureTime's lower bound. |  | Yes | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-15 | duration | Optional (0-1) | IVL_PQ | The duration for this procedure |  | Add to RespiratoryCareProposal | n/a | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-07 | Questionable use case. Also redundant as it is currently addressed in ProcedureProposal by proposedProcedureTime if both bounds are provided. |  | Yes | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-16 | priority | Optional (0-1) | CD | Priority to which a proposed procedure is assigned | Routine, Urgent, Stat | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-07 | Already covered by criticality in ProcedureProposal. |  | Yes | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-17 | prnReason | Optional, Multiple (0-*) | CD | Indication for the proposed procedure such as shortness of breath; Reasons such as "SpO2 less than x%" should be addressed as a PRN Instruction rather than a PRN Reason as it is unlikely that a value set can be identified for such range of possible observations. For example, Pain, Shortness of Breath, Insomnia, Nausea. | Shortness of breath | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-08 | Decided to move PRN Reason to level of procedure proposal instead. It will be inherited by the RespiratoryCareProposal subclass. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-18 | precaution | Optional (0-1) | CD | For example 'Bleeding', 'Chemotherapy', 'Cleft Palate Precautions', 'Latex', 'Radiation', 'Safety Precautions', 'Seizure', 'Spinal Precautions', 'Suicide', 'Total Hip Precautions', 'Aspiration', 'Low Stimulation Precautions', 'Reflux','Bone marrow','Burn', 'Femoral nerve block', 'Hip', 'Protective', (Neutropenic), 'Popliteal nerve block', 'Thrombocytopenic' | For example 'Bleeding', 'Chemotherapy', 'Cleft Palate Precautions', 'Latex', 'Radiation', 'Safety Precautions', 'Seizure', 'Spinal Precautions', 'Suicide', 'Total Hip Precautions', 'Aspiration', 'Low Stimulation Precautions', 'Reflux','Bone marrow','Burn', 'Femoral nerve block', 'Hip', 'Protective', (Neutropenic), 'Popliteal nerve block', 'Thrombocytopenic' | Add to RespiratoryCareProposal | n/a | Victor Lee | RespiratoryCareProposal | Rejected | 2013-03-07 | I believe this is redundant with isolationCode |  | Yes | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
RCP-19 | peakInspiratoryPressure | Optional (0-1) | IVL_PQ | Specification of the maximum airway pressure allowed to be delivered by the ventilator in order to prevent barotrauma, applies to volume-controlled ventilation modes. For example, 35 cmH2O. | 35 cmH2O | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Howard Strasberg | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-08 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-2 | IPAP | Optional (0-1) | IVL_PQ | Inspiratory positive airway pressure, often expressed in cmH20 in the United States. For example, 10 cmH2O | 10 cmH2O | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-20 | inspiratoryTime | Optional (0-1) | IVL_PQ | Specification of the duration of the positive airway pressume applied by a mechanical ventilator. For example, 1 second. | 1 second | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Howard Strasberg | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-08 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-21 | peakFlowRate | Optional (0-1) | IVL_PQ | Specification of the maximum allowable rate of airflow delivered by a mechanical ventilator. For example, 60 L/min. | 60 L/min | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Howard Strasberg | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-08 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-3 | PEEP | Optional (0-1) | IVL_PQ | Positive end expiratory pressure, the alveolar pressure above atmospheric pressure that exists at the end of expiration, often expressed in cmH20 in the United States. For example, 5 cmH2O. | 5 cmH2O | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-4 | fiO2 | Optional (0-1) | IVL_PQ | Fraction of inspired oxygen, expressed as a percentage. For example, 100%. | 1 | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-5 | spO2Range | Optional (0-1) | IVL_PQ | Target oxygen saturation, expressed as a percentage. For instance, 95-100% | 95-100% | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-6 | spO2Titration | Optional (0-1) | string | Titration instructions to achieve target oxygen saturation. An example might include: "Titrate oxygen to maintain SpO2 > 93%" | Titrate oxygen to maintain SpO2 > 93% | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-7 | respiratoryRate | Optional (0-1) | IVL_PQ | Number of machine-delivered breaths per minute, in the context of mechanical ventilation, expressed as breaths/minute. For example, 14 breaths/minute. | 14 breaths/minute | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-8 | tidalVolume | Optional (0-1) | IVL_PQ | Volume of air delivered with each machine-delivered breath, often expressed in mL in the United States. For example, 500 mL. | 500 mL | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes |  | Claude Nanjo | David Shields |  | Pending Review | Phase 1
RCP-9 | pressureSupport | Optional (0-1) | IVL_PQ | Specification of the additional amount of pressure that is added to a mechanical ventilation mode, often CPAP mode. Not to be confused with pressure control ventilation mode. For example, 500 mL | 10 cm H2O | Add to RespiratoryCareProposal | Common attribute associated with certain types of respiratory orders. | Victor Lee | RespiratoryCareProposal | In-Scope for Phase 1 | 2013-03-07 |  |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAB-1 | deliveryMethod | n/a | n/a | Methodology used to administer the substance. E.g., gastric feeding tube, gastrostomy, drip. |  | Add 'drip' as an example in the definition of the item. | Clarify the relationship between SubstanceAdministrationBase and ComplexIVProposal subtype. | Victor Lee | SubstanceAdministrationBase | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAB-2 | dose | Add to SubstanceAdministrationBase a dose attribute of type 'Dose'. | Dose | The amount of a substance administered as well as the type of dose. For instance, one may administer a loading dose followed by a maintenance dose. | Loading Dose, Maintenance Dose, etc... | Add dose to vMR and remove doseType and doseQuantity. | A given SubstanceAdministrationProposal may have multiple doseQuantities each with a different 'doseType'. For instance, you could have a starting dose, a demand dose, etc... | Claude Nanjo | SubstanceAdministrationBase | Rejected | 2013-03-13 | See DT-4 | This requirement will impact backward compatibility. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAB-3 | doseType | Optional (0-1) | CD | The kind of dose. E.g., initial, maintenance, loading. | n/a | Remove doseType from vMR. | Replaced by dose of type 'Dose'. Refer to SAB-2 for the change rationale. | Claude Nanjo | SubstanceAdministrationBase | Rejected | 2013-03-13 | See 'Change Rationale' column. | This requirement will impact backward compatibility. Commented out for now in XSD | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAB-4 | doseQuantity | Optional (0-1) | IVL_PQ | The amount of substance. E.g., 1 tab, 325 mg, 1-2 tabs. | n/a | Remove doseQuantity from vMR. | Replaced by dose of type 'Dose'. Refer to SAB-2 for the change rationale. | Claude Nanjo | SubstanceAdministrationBase | Rejected | 2013-03-13 | See 'Change Rationale' column. | This requirement will impact backward compatibility. Commented out for now in XSD | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAB-5 | frequency | Optional (0-1) | CD | The interval for medication administration. For instance, TID, BID, q8h, etc... | TID, q8h, qac, etc... | Add to SubstanceAdministrationBase | Often providers define frequency using codes. | Claude Nanjo | SubstanceAdministrationBase | Deferred for Phase 2 | 2013-03-06 | This change has significant impact on backward compatibility and requires careful thought on how to express consistently within the vMR. There are also ISO21090 datatypes that address this concept quite well. The group felt that this is a Phase 2 change. | We have found that most of our customers have frequency as an attribute of medication and non-medication orders. Frequency is generally a coded field and associated with value sets specifying frequencies such as ‘TID’, ‘BID’, ‘q2h’, etc… Today, in the vMR, frequency is handled differently for medications and procedures and does not support coded fields. So, ‘TID’ may be represented in the vMR as a number of times (e.g., 3) you do the thing in a 24hr period and whether the time interval is important. For instance, give this to the patient three times a day and wake them up if they are sleeping (time interval is important). It cannot capture instructions such as ‘Four times daily before meals and at bedtime’ though this could be captured with an instruction to the provider along with a frequency of 4 x in 24hrs, interval is not important. However, there are some potential shortcomings that we may need to address in Phase 1 or Phase 2: 1. The representation of frequency differs between SubstanceAdministration and Procedures. a. For SubstanceAdministration i. It is defined in the base class: SubstanceAdministrationBase ii. It is represented by 2 fields: dosingPeriod (IVL_PQ) and dosingIntervalIsImportant (BL) where dosingPeriod seems to represent how often you do the procedure and dosingIntervalIsImportant specifying whether it is TID or q8h. iii. The time interval is fixed as a 24hr time interval (I think). So for procedures that have to be done every, say, 48 hours, I am not sure how you would represent these (dosing period = 0.5?) b. For ProcedureProposal, a subclass of ProcedureBase, we have the following: i. RepeatNumber (how often you do the thing) ii. ProposedProcedureTime (the overall duration – not necessarily 24 hrs and modeled as an IVL_TS rather than a PQ or IVL_PQ) iii. We do not have the equivalent of timePeriodIsImportant. iv. Also, only ProcedureProposal benefits from frequency. So, it may not be possible to document frequency in a ProcedureEvent if it was different than in the procedure proposal. 2. We currently don’t support coded frequencies. a. Most CPOE systems represent frequencies through codes. b. Codes are not easy to compute though but great for information exchange if a value set exists. They require mapping to logic – for instance, q8h = 3 x in 24hr where intervalIsImportant = true. What we need for Phase 1: “Define frequencies for non-med orders” We could achieve this in Phase 1 as follows: 1. Add a Coded frequency field to procedureProposal such as frequency (CD) 2. Add a timeIntervalIsImportant to ProcedureProposal (BL). 3. This does not impact backwards compatibility but is not consistent nor clean. What I think we should do or discuss even if deferred for Phase 2: 1. Find a solution that is consistent for Meds/Non-Meds 2. Support coded frequencies, even if optionally 3. Allows frequency to be computable 4. Does not limit frequency to a 24hr time interval Proposal: 1. Add a frequency type which consists of: a. A repeat number – number of times to do X (INT) b. A duration – within duration (PQ if it is fixed or IVL_PQ if it is a range – e.g. q3h – q4h) c. A flag to indicate whether the interval is important (BL) d. An optional code to represent the computable form as a code ‘TID’, ‘q8h’, etc… (CD) 2. Use this type for both Medications and Non-Medications and place it in the base type in both. a. E.g., ProcedureBase.frequency: Frequency (0..1) | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
SAB-6 | dosingPeriod | n/a | n/a | Together with dosingPeriodIntervalIsImportant, identifies the frequency of substance administration. dosingPeriod identifies the periodicity of doses within a specified timeframe, which is often 24 hours (but may be different for some uses). E.g., a dosingPeriod of 3 times every 24 hrs would signify q8h if dosingPeriodIntervalIsImportant is true, and TID if dosingPeriodIntervalIsImportant is false. Other possibilities include 20 minutes every 2 hours for an infusion, or 30 minutes every 2 days for a medicated compress, etc. | n/a | Change definition | Definition currently states that the period if fixed to 24hrs. This is really just an example. | David Shields | SubstanceAdministrationBase | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | David and Ken to provide new definition for field. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAB-7 | dosingPeriodIsImportant | n/a | n/a | Together with dosingPeriod, identifies the frequency of substance administration. dosingPeriod identifies the periodicity of doses within a specified timeframe, which is often 24 hours, whereas dosingPeriodIntervalIsImportant identifies whether doses should be equally spaced within that timeframe. E.g., a dosingPeriod of once every 8 hr would signify q8h if dosingPeriodIntervalIsImportant is true, and TID if dosingPeriodIntervalIsImportant is false. | n/a | Change definition | Definition currently states that the period if fixed to 24hrs. This is really just an example. | David Shields | SubstanceAdministrationBase | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | David and Ken to provide new definition for field. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAE-1 | isValid | Optional (0-1) | BL |  |  | Remove from SAE | Moved to AS. See AS-1. | David Shields | SubstanceAdministrationEvent | Deferred for Phase 2 | 2013-03-08 |  | Seek feedback from immunization registry experts. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
SAP-1 | originationMode | Optional (0-1) | CD | The mode the order was received (such as by telephone, electronic, verbal, written). This describes 'how' the communication was done as opposed to dataSourceType which specifies the 'where' and 'from'. | Telephone, verbal, written, electronic | Add originationMode to SubstanceAdministrationProposal. | Defined in CIMI model. Describe how the order proposal was received. | Victor Lee | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | Here we discussed how originationMode differs from dataSourceType. The datasource if often needed for CDS - who asked for this order. It lends weight to the request. OriginationMode specifies the 'how'. How was it communicated? | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAP-10 | PCA | n/a | Extends SubstanceAdministrationProposal | Order represents a Patient Controlled Analgesic. For instance, morphine PCA, 5 mg loading dose, followed by 10 mg/hr basal rate, 1 mg demand dose, lockout interval 10 min. | morphine PCA, 5 mg loading dose, followed by 10 mg/hr basal rate, 1 mg demand dose, lockout interval 10 min | Introduce PCA subclass of SubstanceAdministrationProposal | PCA orders are specialization of SubstanceAdministrationProposal. | Claude Nanjo | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-08 | See 'Change Rationale' column. | Do we really need this or should we simply move its fields to SubstanceAdministrationProposal or SubstanceAdministrationBase. This may not be relevant to MOST medication orders though. | Yes | Yes | 2013-03-09 | Claude Nanjo | Victor Lee |  | Pending Review | Phase 1
TUB-2 | dosingGoal | Optional (0-1) | IVL_PQ | Target tube feeding rate | 75 ml/hour | Add to TubeFeedingProposal | Common tube feeding attribute. | Victor Lee | TubeFeedingProposal | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | Victor Lee |  | Pending Review | Phase 1
TUB-3 | dosingRateIncrement | Optional (0-1) | IVL_PQ | Change in the dosing rate; usually an increase for a patient who is initiating tube feeding | 20 ml/hour | Add to TubeFeedingProposal | Common tube feeding attribute. | Victor Lee | TubeFeedingProposal | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | Victor Lee |  | Pending Review | Phase 1
TUB-4 | dosingRateIncrementInterval | Optional (0-1) | IVL_PQ | Period of time after which the dosingRateIncrement should be attempted | 4 hours | Add to TubeFeedingProposal | Common tube feeding attribute. | Victor Lee | TubeFeedingProposal | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | Victor Lee |  | Pending Review | Phase 1
SAP-11 | timing | Optional (0-1) | CD | Timing relative to some event. Today, Tomorrow, On Admission to ICU, etc... | Today, Tomorrow, On Admission to ICU, etc... | Add to SubstanceAdministrationProposal. | Common attribute for this type of orders | Howard Strasberg | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAP-12 | lockoutInterval | Optional (0-1) | IVL_PQ | The amount of time that must elapse after a PCA demand dose is administered before the next PCA demand dose can be delivered. For example, 10 minutes | 10 minutes | Add under SubstanceAdministrationProposal. | Common PCA proposal field. | Victor Lee | SubstanceAdministrationProposal | Rejected | 2013-03-11 | Group decided to keep PCA orders as subclass even though it has a single attribute. | May need to revisit this in Phase 2 as we learn more about templates. | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAP-13 | validAdministrationTimeInterval | Optional (0-1) | IVL_TS |  |  | Remove from SAP | Moved to AS. See AS-2. | David Shields | SubstanceAdministrationEvent | Deferred for Phase 2 | 2013-03-08 |  | Seek feedback from immunization registry experts. | n/a | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
SAP-14 | ComplexIVProposal | n/a | n/a | A class representing IV fluids that may consist of one or more diluents and additives. | DOPamine drip 800mg/500mL D5W | Extend SubstanceAdministrationProposal | IVs are very common components of order sets. Rather than define these as related clinical statement, IVs require a class of their own. Premixes can be represented as standard SubstanceAdministrationProposals. | Claude Nanjo | ComplexIVProposal | In-Scope for Phase 1 | 2013-03-11 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-11 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAP-2 | orderJustification | Optional (0-1) | CD | Taken from CIMI: OrderJustification is a component model. Order Justification lists any required items to explain the why's of the order. This is not a semantic link because the justification is made at the time of the order by the practitioner and alterable by the practictioner. Billing may use this justification, but billing cannot create this justification. Any justification created in the billing use cases will need to be of a different structure. Current values for the key domain are: Diagnosis, Signs and Symptoms, ?Health Issue. Action in the application will be: A practictioner may choose justification from a list or from the problem list of the patient. If the practictioner chooses a problem from a list then the application will ask: do you want to add this to the patient's problem list? If yes then the problem will be create in a model structure, if no then the ecid for the Health Issue will be stored. Because the Health Issue domain is not sub categorized we perform the categorization of the health issue via the key domain chosen. This way the order application and the data mining efforts can find what kind of thing this is being used as. Kind of a role. The otherwise error line exists because this model is meant for application use and should have an expectation of what is allowed. |  | Add orderJustification to SubstanceAdministrationProposal | Often a proposal is backed by information about the patient. For instance, a proposal may be justified by a problem from the patient record. | Claude Nanjo | SubstanceAdministrationProposal | Rejected | 2013-03-06 | This is already addressed in the vMR using related clinical statements. Note that even the CIMI description describes such an approach. The group agrees that related clinical statements is a more elegant approach than simple codes. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAP-3 | comment | Optional, Multiple (0-*) | Documentation | A comment, instruction, or note associated with the proposal. The type specifies the type of comment (e.g., 'Provider Instruction', 'Patient Instruction', 'Reason for Procedure', 'Consult Note', etc...) and the value of the comment represents the free text value. | provider instructions, patient instructions, notes, etc... | Add comment to SubstanceAdministrationProposal. Make type of comment 'Document' and introduce 'Document as a new type. | Order proposals often have associated comments. Comments may be addressed to different target audiences and thus a comment type provides additional information about the purpose of the comment. A comment can be restricted to be free text in a template or could support other formats such as XML, PDFs, etc.... | Victor Lee | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | General way to represent comments of various types. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAP-4 | providerInstructions | Optional, Multiple (0-*) | string | From CIMI: ProviderInstruction This field contains the ordering provider's instructions to the patient or the provider administering the drug or treatment. (HL7 definition, RXE-7) This is called Directions in Centricity Pharmacy which creates an English translation of the dose and frequency which then can be added to or changed by the pharmacist. | n/a | Add to SubstanceAdministrationProposal. | Provider Instructions is a common attribute of orderables. | Claude Nanjo | SubstanceAdministrationProposal | Rejected | 2013-03-06 | Can be modeled more generically using the Documentation type. Refer to PP-3 for more information about this approach. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAP-5 | specialHandling | Optional, Multiple (0-*) | CD | From CIMI: SpecialHandling Built to accomodate special conditions in execution of the order. Particularly in transportation and radiology type orders. Such as diabetes, fractures(s), fragile skin, Isolation, No special handling, nurse to assist, etc... | diabetes, fractures(s), fragile skin, Isolation, No special handling, nurse to assist, etc... | Add to SubstanceAdministrationProposal. | special handling is often an attribute of orderables. | Claude Nanjo | SubstanceAdministrationProposal | Rejected | 2013-03-06 | Not that relevant to SubstanceAdministrationProposal. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAP-6 | orderStatus | Optional (0-1) | CD | State of this proposal in the workflow. Note that the set of relevant states may vary by type of proposal. (e.g., the workflow on a laboratory proposal may be different from the workflow for substance administration proposals.) | VL: I am not sure about examples | Add to SubstanceAdministrationProposal. | The purpose of this element is to support workflow. | Claude Nanjo | SubstanceAdministrationProposal | Deferred for Phase 2 | 2013-03-11 | See 'Change Rationale' column. VL: I cannot think of a use case for this data element, as I've never had to specify when entering orders. Even if there is a use case, it might be uncommon enough that we'd ask implementers to use an extension mechanism to capture. | Omit for Phase 1, reconsider for Phase 2 if there is a use case defined by the community | No | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
SAP-7 | isPrn | Optional (0-1) | BL | Is order a PRN order |  | Add to SubstanceAdministrationProposal. | Provider Instructions is a common attribute of orderables. | Claude Nanjo | SubstanceAdministrationProposal | Rejected | 2013-03-07 | Redundant with prnReason |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
SAP-8 | prnReason | Optional, Multiple (0-*) | CD | Indication for the proposed procedure such as shortness of breath; Reasons such as "SpO2 less than x%" should be addressed as a PRN Instruction rather than a PRN Reason as it is unlikely that a value set can be identified for such range of possible observations. For example, Pain, Shortness of Breath, Insomnia, Nausea. | Pain, Shortness of Breath, Insomnia, Nausea | Add to SubstanceAdministrationProposal. | PRN Reason is a very common attribute of medication orderables. | Victor Lee | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. | Please note the proposed usage for PRN Reason. PRN Reason is a coded field. For most cases this is a valid assumption. In some cases, the PRN Reason may be based on some observation of the patient and could be stated in either free text or as a related observation. In these cases, the PRN Reason value set should offer a choice of 'Other' and either a comment of type 'PRN Instruction' or a related clinical statement of type 'PRN Reason' should be associated with this proposal. | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SAP-9 | infuseOver | Optional (0-1) | IVL_PQ | Represents the actual time the medication is infused. Note the difference between infuseOver and duration. An orderable may call for infusing a patient TID for an hour each time over a duration of 5 days. For example, 1 hour. | 1 hour | Add to SubstanceAdministrationProposal. | infuseOver is common to some common type of volume-based medication orderables. | Victor Lee | SubstanceAdministrationProposal | In-Scope for Phase 1 | 2013-03-06 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SCM-1 | source | Optional (0-1) | CD | The specimen source. E.g., sputum, urine, blood, stool |  | Add to Specimen class. | Important specimen attribute | Claude Nanjo | Specimen | In-Scope for Phase 1 | 2013-03-07 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-09 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
SCM-2 | description | Optional (0-1) | string | Text to describe the specimen. |  | Add to Specimen class. | Important specimen attribute | Claude Nanjo | Specimen | Rejected | 2013-03-07 | Group could not properly define or identify use cases for this field. |  | n/a | n/a | n/a | n/a | n/a | n/a | Rejected | n/a
TUB-1 | TubeFeedingProposal | n/a | Extends SubstanceAdministrationProposal | A class representing enteral nutrition proposals for the delivery of tube-fed substances (eg, Nutren, Ensure, RenalCal) for patients who are unable to consume diets orally; tube feedings can be delivered to the stomach or varying parts of the small intestines using a variety of tube placement methods, depending on the clinical scenario. | Nutren via nasogastric tube, 20 ml/hour, increase by 20 ml every 4 hours, goal of 75 ml/hour, water flushes 125 ml every shift | Add to model by extending SubstanceAdministrationProposal | Common nutrition order | Victor Lee | TubeFeedingProposal | In-Scope for Phase 1 | 2013-03-12 | See 'Change Rationale' column. |  | Yes | n/a | n/a | n/a | n/a | n/a | Deferred | Phase 2
GB-2 | importance | Optional (0-1) | CD | The clinical importance or seriousness of the adverse event. E.g., life-threatening, potentially requires hospitalization, self-resolving. Different from severity in that a moderate subarachnoid hemorrhage is likely to be highly important, whereas a moderate headache is not. |  | Add to GoalBase | Needed to disambiguate semantics of Criticality. | Mark Roche | GoalBase | In-Scope for Phase 1 | 2013-03-12 | See 'Change Rationale' column. | Note that not everywhere 'criticality' was specified ambiguously did we add importance. Hence, when reviewing the vMR,if there are cases where importance is needed, please be sure to make the recommendation to the vMR group. | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CSERR-1 | targetRole | Required (1-1) | CD | The relationship between a ClinicalStatement and an Entity serving the indicated function or position. |  | Rename role to targetRole | Needed to align this association class with EntityRelationship | David Shields | ClinicalStatementEntityInRoleRelationship | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | Yes | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1
CSERR-2 | relationshipTimeInterval | Optional (0-1) | IVL_TS | The timeframe in which the relationship existed. |  | Add to ClinicalStatementEntityInRoleRelationship | Needed to align this association class with EntityRelationship | David Shields | ClinicalStatementEntityInRoleRelationship | In-Scope for Phase 1 | 2013-03-13 | See 'Change Rationale' column. |  | Yes | n/a | 2013-03-13 | Claude Nanjo | David Shields |  | Pending Review | Phase 1